## riskassessment-assessment 1
Security Risk Assessment
Risk # | Risk | Risk Family | Control | Likelihood | Impact | Reasoning | Mitigating Controls | Total Risk Score
1 | Weak Encryption | Data Security | VPC3 File storage only supports AES-128 Encryption | Very Low | High | Although its impact is high, Its unlikley for a threat actor to target a VPC3 file storage. | Placeholder Assume none | Moderate
2 | Unencrypted data | Data Security | Databases in production are unencrypted | Medium | Very High | Unencrypted databases are considered bad practice because threat actors are always looking for data, and if they exploit it, the impact of leaking those data is very high. | Placeholder Assume none | Critical | Risk Matrix
3 | Easily guessed password | Access Security | Internal network users require a 7-character password | Very Low | Medium | Even though the likelihood of this risk is very low, it still has a medium impact because organizations should always keep an eye out for internal threats. | Placeholder Assume none | Sustainable | Impact |  | Very Low | Low | Medium | High | Very High | Likelihood | Impact
4 | Risk of leaked password | Access Security | Passwords never expire | Medium | High | Passwords should be changed frequently because if any information leakage happens, all users data and privileges will get exploited. | Placeholder Assume none | Severe | Likelhood | Very High | Moderate | Severe | Severe | Critical | Critical | Very High | Very High
5 | Risk of brute force | Access Security | VPN Access does not require MFA | Low | Medium | VPN MFA is a good practice to add as an extra layer of protection for the system, it's unlikely to get exploited even though it has a medium impact. | Placeholder Assume none | Moderate |  | High | Sustainable | Moderate | Severe | Critical | Critical | High | High
6 | Weak Encryption | Network Security | TLS V1.1 is used between the cloud production environment and SwiftTechâ€™s physical location | Low | Very High | Although implementing an encryption protocol is considered as good practice, it will have a very high impact since it is related to cloud security. | Placeholder Assume none | Critical |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | Medium | Medium
7 | No segmentation for application layers | Application Security | Application development Tiers are not logically segmented from Business Application servers | Medium | High | Application should always consist of three tiers, because threat actors are always looking for application to exploit, and if application development tiers are not segmented from application servers, the impact of one layer getting compromised and affecting the other layer is high. | Placeholder Assume none | Severe |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | Low | Low
8 | Unprotected System | System Security | Development Tier servers are unpatched and contain multiple vulnerabilities | Low | Very High | Systems should always get updated, even though it's unlikely for them to get exploited, because the impact of this vulnerability is very high and might cause multiple threats. | Placeholder Assume none | Critical |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | Very Low | Very Low
9 | Secure code practice is not implemented | Application Security | Application code is not scanned for vulnerabilities before being published into production environment | Medium | Very High | Applications should always get their code scanned for vulnerabilities, and since it will be released in production, the likelihood of this risk is medium, and the impact of exploiting this vulnerability is very high. | Placeholder Assume none | Critical
Notes:
Risk - descriptions should be some reasonable approximation of what is written above but does not need to be exact
Reasoning - The reasoning should approximately match to the user's assessment of the likelihood and impact of a potential risk. If, for instance the likelihood and impact are marked high, the reasoning should reflect why it might be high
Mitigating Controls - For the purpose of this exercise we did not include mitigating controls
Total Risk Score - Should not be less than a reasonable approximation of the likelihood x impact. For instance, if L=High and I=High (and no mitigating control exists) then Risk cannot equal Low